Legacy Prime Workflow Suite

Implementation Plan, Delivery Schedule & Requirements

Date: March 25, 2026

Project Overview

This document outlines the full implementation approach, week-by-week delivery schedule, and everything required from you before and during development. Each section is written in plain terms — no technical language.

Total Development Timeline

3.5 weeks

Android live on Google Play

Week 4 (pending Google review)

What We Need From You — Master Checklist

Every decision, credential, and account we need from you, grouped by when they are needed so nothing blocks development at the wrong time.

What We Need

Details

Needed By

DECISIONS — YOU CONFIRM THE NUMBERS

Subscription pricing per tier

Monthly dollar amount for each employee bracket (1-5 users = $X/mo, 6-15 = $X/mo, 16-30 = $X/mo, etc.)

Week 3

Setup / onboarding fee

One-time fee at signup in addition to monthly? If yes — how much?

Week 3

Free trial period

How many days before first charge? (e.g. 14 days, 30 days, or none)

Week 3

Existing companies on the platform

Companies that already paid the one-time fee — grandfathered into new system or migrated to monthly plan?

Week 3

Your owner account email

Which email is your Super Admin / Owner login? This account gets exclusive access to the owner panel.

Before Week 1

ACCOUNTS — YOU CREATE OR PROVIDE ACCESS

Google Cloud Console access (Maps API key)

Access to generate a Maps API key — same account connected to your Firebase project. Without this, maps cannot display.

Before Week 1

Firebase project access (Android push notifications)

Download the Android configuration file. Without this, Android users will NOT receive push notifications.

Before Week 4

Google Play Developer Account

One-time $25 fee paid directly to Google at play.google.com/console. Share access if you already have one.

Before Week 4

Stripe live account access

To create subscription products and pricing plans inside your Stripe dashboard for recurring billing.

Week 3

CONTENT — YOU PROVIDE OR APPROVE

Privacy policy URL

Required by Google Play before app approval. Must be a live, accessible web link.

Before Week 4

App store description (Android)

Short and long description for the Google Play listing. We can draft this for your approval.

Week 4

⚠  Important Note — Push Notifications: During our audit we identified that your push notification credentials are configured in the code but have not been added to your live server environment. This means push notifications may already be failing silently in production. We will fix this at the start of Week 1 as part of the GPS work at no additional cost.

Execution Order & Why It Matters

•	GPS Tracking is independent — starts immediately on Day 1

•	Super Admin → Employee Limits → Billing are built in sequence. Each one depends on the previous. You need the admin panel before you can control billing, and billing controls the user limits

•	Android comes last so it launches with all features complete and fully working

Week 1  —  Days 1 through 5

GPS Location Tracking  (Days 1–3)

What gets built:

•	Every clock event (clock in, lunch start, lunch end, clock out) captures the employee's exact GPS coordinates at that moment

•	Each time entry in the timecard history shows a small embedded map with a pin for exactly where the employee was

•	Your dashboard gets a live map showing all currently clocked-in employees across your projects

Requires from you before Day 1: Google Cloud Console access so we can generate the Maps API key

What you can test by end of Day 3: Clock in as an employee, perform all clock actions, then open the timecard — you will see a map pin for every single event.

Super Admin Panel — Foundation  (Days 4–5)

What gets built:

•	Backend infrastructure that allows your owner account to see data across all companies without any company seeing another's data

•	Security layer built and verified before the UI is added

Requires from you before Day 4: Confirmation of your owner account email address

Week 2  —  Days 6 through 10

Super Admin Panel — Complete  (Day 6)

What gets built:

•	Company list showing every business on your platform with their user count, active projects, subscription plan, and payment status

•	Individual company controls — click into any company to adjust their plan, pricing, user limit, or activate/suspend their account

•	Fully hidden from all regular users — only your owner account can see it

What you can test by end of Day 6: Log in with your owner account and see every company. Click into one, change their plan, and suspend their account.

Employee Count Control  (Days 7–8)

What gets built:

•	System blocks new users from being added when a company hits their limit

•	Admins see a clear 'X of Y employees used' indicator in their team management screen

•	Upgrade prompt appears automatically when the limit is hit

•	Limit updates automatically when a company upgrades their subscription

What you can test by end of Day 8: Set a company to a 3-user limit and try adding a 4th — the system blocks it and shows the upgrade prompt.

Subscription & Billing — Start  (Days 9–10)

What gets built this week:

•	Stripe pricing tiers created for each employee count bracket

•	The current one-time payment system begins conversion to monthly recurring

Week 3  —  Days 11 through 15

Subscription & Billing — Complete  (Days 11–14)

What gets built:

•	Companies billed automatically every month — no manual action needed from you

•	Failed payment automatically suspends the account. Successful payment automatically reactivates it

•	Optional one-time setup fee collected at signup alongside first monthly payment

•	Your owner panel shows all payment statuses and total monthly revenue

•	Companies can update their own payment method or view invoices from inside the app

•	You can override any company's pricing from your admin panel at any time

Requires from you before Day 11:  Confirmed pricing amounts per tier  •  Decision on setup/onboarding fee (yes/no and amount)  •  Decision on free trial period length  •  Decision on existing company migration  •  Stripe live dashboard access

What you can test by end of Day 14: Complete a full signup, pay a subscription, then simulate a failed payment — watch the account suspend and reactivate automatically.

Android Setup & Configuration  (Day 15)

What gets built:

•	Android build system configured with production signing

•	Firebase Android push notification connected

•	Login screen corrected for Android (Apple Sign-In replaced with Google Sign-In on Android devices)

Week 4  —  Days 16 through 20

Android Testing & Bug Fixes  (Days 16–18)

What happens:

•	First Android build installed on real Android devices

•	Every major feature tested: login, GPS clock-in, photo uploads, push notifications, team chat, audio/video messages, document uploads, and Stripe payment

•	All Android-specific issues found during testing are resolved

Requires from you before Day 16:  Firebase project access (Android push notifications)  •  Google Play Developer Account created ($25 to Google)  •  Privacy policy live at a public URL

Google Play Store Submission  (Days 19–20)

What gets done:

•	Store listing created with app description, Android screenshots, app icon, and all required Google information

•	Submitted to Google Play for review

•	Internal test track verified before public release

Requires from you before Day 19: Approval of app store description (we draft, you approve)

Full Timeline Summary

Week

What Gets Done

Deliverable

Week 1

GPS Location Tracking (3 days)

Super Admin Panel — backend foundation (Days 4-5)

GPS + maps live

Week 2

Super Admin Panel — complete (Day 6)

Employee Count Control (Days 7-8)

Subscription & Billing — begin (Days 9-10)

Owner panel live

Limits enforced

Week 3

Subscription & Billing — complete (Days 11-14)

Android setup & configuration (Day 15)

Recurring billing live

Week 4

Android testing & bug fixes (Days 16-18)

Google Play submission (Days 19-20)

Submitted to Google

Post Week 4

Google review (1-3 business days — Google's timeline)

Android live on Google Play Store

TOTAL

3.5 weeks

Feature Summary

#

Feature

What It Does

Timeline

1

GPS Location Tracking

Capture + map display on every clock event

3 days

2

Super Admin Panel

Private owner dashboard — manage all companies

2.5 days

3

Employee Count Control

Enforce user limits per plan, prompt to upgrade

2 days

4

Subscription & Billing

Full automated monthly billing via Stripe

4 days

5

Android Build & Deployment

Full Android version live on Google Play

1 week + store review

TOTAL

3.5 weeks

Requirements — Timeline View

What We Need

Wk 1

Wk 2

Wk 3

Wk 4

Your owner account email (Super Admin login)

✦

Google Cloud Console access (Maps API key)

✦

Stripe live dashboard access

✦

Subscription pricing amounts per tier

✦

Setup/onboarding fee decision (yes/no + amount)

✦

Free trial period length

✦

Existing company migration decision

✦

Firebase project access (Android notifications)

✦

Google Play Developer Account ($25 to Google)

✦

Privacy policy live at a public URL

✦

App store description approval

✦

✦  Required before Week 1 (critical path)

✦  Required by indicated week

Notes

•	All work is done on your live codebase — nothing is rebuilt from scratch

•	You can test each feature the moment it is complete — we do not wait until everything is done

•	The Android Google review period is outside our control — we submit, Google decides when to approve

•	Stripe pricing amounts are entirely your decision — we build whatever structure you confirm